## Jayati
Sprint 1
February 10 to February 19 |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday
Tasks | Start Hours | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Total
Study of Research Papers | 25 | 0 | 0 | 4 | 4 | 4 | 5 | 0 | 4 | 0 | 25
Install Libraries | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5
Data Collection | 40 | 0 | 0 | 0 | 4 | 4 | 4 | 8 | 4 | 4 | 28
Actual Reamining Time | 60 | 60 | 60 | 51 | 43 | 35 | 26 | 18 | 10 | 6
Estimated Reamning Time | 60 | 53.4 | 46.8 | 40.2 | 33.6 | 27 | 20.4 | 13.8 | 7.2 | 0
Sprint 2
February 20 to February 28 |  | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
Tasks | Start Hours | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Total
Data Cleaning (Noise) | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
GUI mutiple window error | 35 | 5 | 3 | 2 | 0 | 5 | 5 | 5 | 5 | 5 | 35
Classified Dataset | 9 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 9
Separate into Test and Train Data | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2
Actual Reamining Time | 50 | 45 | 37 | 35 | 35 | 27 | 19 | 11 | 5 | 0
Estimated Reamning Time | 50 | 44.5 | 39 | 33.5 | 28 | 22.5 | 17 | 11.5 | 6 | 0
Sprint 3
March 2 to March 13 |  | Monday | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday | Friday
Tasks | Start Hours | Day 15 | Day 14 | Day 13 | Day 12 | Day 11 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Total
GUI (tk) | 15 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GUI framesets, buttons | 40 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 10 | 5 | 0 | 40
Documentation (PPT, Sprints) | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5
Actual Reamining Time | 60 | 53 | 46 | 39 | 35 | 31 | 26 | 21 | 11 | 6 | 1
Estimated Reamning Time | 60 | 54 | 48 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0